## UAT BUGS REPORT
Project Name: |  | Bhutan Biosecurity and Food Safety System
Department: |  | Bhutan Agriculture and Food Regulatory Authority
Sl No. | Change in Brief | Description in details | Requested By | Requested Date | Type (Bug/Change Request) | Status (Open/Close) | Remarks
1 | Import of Plants and Plant Products | To synergize with the existing RAMIS system for collection of revenue, BAFRA to provide contact numbers of relevant section official in each dzongkhag and field office designated for collection revenue |  | 16/08/2021 | Change Request | Open | new reqirement
2 |  | Under the import application dash board of assigned inspector, the quantity rejected field should reflect the actual quantity rejected from the total quantity released. the feature should be also able to reflect the balance quantity which the importer can apply for next shipment within the validity period of the import permit. When the quantity is zeroed, the importer should process for new import permit. |  | 2021-08-16 | Change Request | Open | new reqirement
3 |  | The system should give options to the inspector to choose the area of quarantine, in case the quarantine station in his/her jurisdiction is not feasible for that particular consignment. | Kubir | 16/08/2021 | Change Request | Fixed | though it’s a new reqirement we have taken up the changes since its similar to livestock section
4 | Seed Certification | BAFRA to provide the revised list of notified/released variety of seeds and types of attachments required at the time of application process by the client to the system developer. | Kubir | 16/08/2021 | Change Request
5 |  | Developer to amend the crop categories as horticulture, forestry, ornamental, fodder and integrated. | Kubir | 16/08/2021 | Change Request | Fixed
6 |  | Trade license number in the application forms to be kept optional (i.e. asterisk to be removed in all applicable fields). | Kubir | 16/08/2021 | Change Request | Fixed
7 |  | In the event nursery operator is not able to sale the certified seeds within 9 months (which is the blanket validity period for any seeds), the operator should apply to the concerned BAFRA office for recertification of the remaining seed lot. Seed certificate validity may be extended for next 6 months provided the test reports of the seed meet the minimum standard requirements | Kubir | 16/08/2021 | Change Request | Open | new reqirement
8 | In-country Movement Permit Plant | Nursery registration number and name of the company/nursery to be removed. | Kubir | 16/08/2021 | Change Request | Fixed
9 |  | CID field to be moved to the top left corner, to enable the client to retrieve information via API system. | Kubir | 16/08/2021 | Change Request | Fixed
10 |  | If the conveyance is via Air, the vehicular number field should be made non-mandatory or disabled. | Kubir | 16/08/2021 | Change Request | Fixed
11 |  | Observation field to be used by the inspector has to be common or one for the entire consignment. Need to amend current system where there is corresponding observation field for each item for the same lot/consignment. | Kubir | 16/08/2021 | Change Request |  | Developers felt that the current feature to add multiple observation meets the requirement
12 |  | Validity and revenue fee features must to be incorporated. Validity period/day should be kept flexible for the inspectors to assign based on the nature of consignment. | Kubir | 16/08/2021 | Change Request | Fixed
13 | Export of plants and plant products | Trade license number to be kept optional | Gyem Bidha | 16/08/2021 | Change Request | Fixed
14 |  | Current application forms are bifurcated into export, direct export and retail categories. Application form has to be redesigned to capture common information for both the export and retail categories (at the top), followed by specific forms for the retail and export purpose (at the bottom). However, in some situation, an applicant may be appliable to fill out application forms for both the categories (export and retail). The application should come in a single page. | Gyem Bidha | 16/08/2021 | Change Request | Fixed
15 |  | Type of Export Certificate to be generated as the output should depend on the application Type, which is either Export Certificate for Retail or Export Certificate for Export | Gyem Bidha | 16/08/2021 | Change Request |  | Waiting for formats
16 |  | BAFRA to provide Retail Export Certificate format to the developer to design certificates in the system. | Gyem Bidha | 16/08/2021 | Change Request |  | Waiting for formats
17 |  | Trade license number to be kept optional for PSC application form | Gyem Bidha | 16/08/2021 | Change Request | Fixed
18 |  | Under unit section, “units” to be removed and has to be replaced with “Nos” instead | Gyem Bidha | 16/08/2021 | Change Request | Fixed
19 |  | Common name is missing as per the application format | Gyem Bidha | 16/08/2021 | Change Request | Fixed
20 |  | Distinguishing mark to be kept optional | Gyem Bidha | 16/08/2021 | Change Request | Fixed
21 |  | Declared point of entry has to be elaborated as “Declared point of entry (of importing country)” in the application form | Gyem Bidha | 16/08/2021 | Change Request | Fixed
22 |  | Comment box for quarantine and regulated non-quarantine to be removed | Gyem Bidha | 16/08/2021 | Change Request | Fixed
23 |  | Scientific name of the pest to be placed under type of pest | Gyem Bidha | 16/08/2021 | Change Request | Fixed
24 |  | Treatment specification to be kept non-mnadatory | Gyem Bidha | 16/08/2021 | Change Request | Fixed
25 |  | Treatment possible to be placed under phytosanitary measures | Gyem Bidha | 16/08/2021 | Change Request | Fixed
26 | Division Name- PABD | It has to changed to PABD from PABO | Kubir | 16/08/2021 | Change Request | Fixed
27 | Food Business Licensing | Licensing Critiera only one- BAFRA GHP/GMP but keep as master data for future additions | Kubir | 16/08/2021 | Change Request | Fixed
28 | Food Business Licensing | Keep village list only for gewogs | Kubir | 16/08/2021 | Change Request | Fixed
29 | Reasons Why Licensing is no longer valid | Enable only when yes for if FBO has been licensed before | Kubir | 16/08/2021 | Change Request | Fixed
30 | Any proceedings from any regulatory authority | Enable only if FBO is commission | Kubir | 16/08/2021 | Change Request
31 | Food Business Licensing | Opening and Closing meeting | Kubir | 16/08/2021 | Change Request | Fixed
32 | Food Business Licensing | Inspector Details changed to Details of Inspecion | Kubir | 16/08/2021 | Change Request | Fixed
33 | Food Business Licensing | Remove forwarding of response to OIC and directly to inspection team | Kubir | 16/08/2021 | Change Request | Open | new requirement. change in process flow
34 | Factory Inspeciton-FSL | Change Concerns to Non-Conformities (Minor/Major) | Kubir | 16/08/2021 | Change Request | fixed
35 | Followu p inspection | Response should not go to OIC, it should go to Inspector team leader | Kubir | 16/08/2021 | Change Request | Open | new requirement. change in process flow
36 | Approval for FSL | Disable Acknowledge on Focal page during approving of food safety license | Gyem Bidha | 16/08/2021 | Change Request | Fixed
37 | Food Safety License | Edition in the format- updated will be shared | Kubir | 16/08/2021 | Change Request |  | Waiting for formats
38 | Food Handlers Licensing | Associated food establishment- | Kubir | 16/08/2021 | Change Request |  | Not Clear
39 |  | optional prefreed dates- options for OIC to fix dates for training, keep only one day training date | Sonam Dolma | 16/08/2021 | Change Request | Open | New Requirement.Change in the Form
40 | Food Handler License | Format for License- include scope, move conditions to back page, printing options for focal officers | Kubir | 16/08/2021 | Change Request | Fixed
41 | NC report for FSL | rewrite: Action to 'Action proposed by the client' | Tashi | 20/8/21 | Change Request | Fixed
42 | Attachments | Allow upload limit of file size | Kubir | 16/08/2021 | Change Request |  | We suggest not to limit the file size
43 | FSL (Conditional clearance, License) , FHL, Export Certificate | Payment before printing of certificates | Kubir | 16/08/2021 | Change Request | Fixed
44 | Under Food Product Certification: Factory details change | Write (If different from above) and keep it as optional | TY/DC/YL | 20/08/2021 | Change Request | Fixed
45 | In all 3 application forms | Insert at the end of Point 1 of application form: Name of the Technical Incharge (if different from the owner): Name of the Management Incharge (if different from the owner): | TY/DC/YL | 20/08/2021 | Change Request | Fixed
46 | Remove * under Product Information | Remove * for Trade Mark, it is optional | TY/DC/YL | 20/08/2021 | Change Request | Fixed
47 | Add details for 'value' | For fields titled 'value', add this in brackets (in Nu.) | TY/DC/YL | 20/08/2021 | Change Request | Fixed
48 | Change save to ' Submit' | At the end of Standards, change 'save' to 'submit' | TY/DC/YL | 20/08/2021 | Change Request | Fixed
49 | Export details (previous and current year) | Keep as optional-remove * | TY/DC/YL | 20/08/2021 | Change Request | Fixed
50 | Questionnaire not available for download | Make the questionnaire available for download, after 'Product Information' and before 'production details' | TY/DC/YL | 20/08/2021 | Change Request | Fixed
51 | File attachment as part of application submission | Write: Reminder to upload the duly filled questionnaire as part of application, Make it * | TY/DC/YL | 20/08/2021 | Change Request | Fixed
52 | Remarks visibility | Remarks typed by Focal Officer not visible by Client | TY/DC/YL | 20/08/2021 | Change Request | Fixed
53 | Team Leader | The remarks from Focal Officer - change to - Remarks from Team Leader | TY/DC/YL | 20/08/2021 | Change Request | Fixed
54 | Team Leader - Audit findings | Remove 'corrective action proposed' | TY/DC/YL | 20/08/2021 | Change Request | Fixed
55 | NC report | 1. Confirmatory Details change to 'Non Conformity Details' 2. Remove: Provisional Audit Date 3. ADD: Root Cause Analysis, Proposed Corrective Action, Proposed completion date, 4. For every NC, give Option to 'respond' | TY/DC/YL | 20/08/2021 | Change Request | Fixed
56 | For all 3 processes | Certificate - Numbering style Certificate - 3 formats (both accredited and non accredited) | TY/DC/YL | 20/08/2021 | Change Request | Fixed
57 | Focal - certificate generate | Choose and select which one to grant - accredited and non accredited | TY/DC/YL | 20/08/2021 | Change Request | Fixed
58 | Final Certificate | Give viewing/printing option to the Focal Officer | TY/DC/YL | 20/08/2021 | Change Request | Fixed
59 | Focal Officer - Certificate | Write 'number of days' in bracket for Validity of Certificate | TY/DC/YL | 20/08/2021 | Change Request | Fixed
60 | Application Number | Option for Focal Officer to update the application number assigned manually. | TY/DC/YL | 20/08/2021 | Change Request | Open | New Requirement
61 | BhutanGAP/Organic | Farmers Group Number - change to - No of members in the group, make * | TY/DC/YL | 20/08/2021 | Change Request | Fixed
62 | Applicant Interface for Food Product Certification | Add name of technical incharge (if diiferent from owner) Add name of management incharge (if differenct from owner) | TY/DC/YL | 20/08/2021 | Change Request | Fixed
63 | Farmer Group deatils | Option to edit/delete | TY/DC/YL | 20/08/2021 | Change Request | Fixed
64 | BhutanGAP and Organic Applicant | For more clarity - Add Crop production details for the last year and crop production details for the current year | TY/DC/YL | 20/08/2021 | Change Request | Fixed
65 | Pack house details | Add option - to click to next if not applicable | TY/DC/YL | 20/08/2021 | Change Request | Fixed
66 | Client - GAP application | Under file attachment - Prelim Questionnaire change to 'INITIAL QUESTIONNAIRE FOR BHUTANGAP FARM ASSESSMENT | TY/DC/YL | 20/08/2021 | Change Request | Fixed
67 | All 3 processes | under Standards, for all 'Disagree' - treat like * so that application cannot be submitted if not agreed | TY/DC/YL | 20/08/2021 | Change Request | Fixed
68 | Audit team detail in GAP/Organic | Audit team detail to be change as Audit team member | TY/DC/YL | 20/08/2021 | Change Request | Fixed
69 | BhutanGAP/Organic - Focal - view | Audit Team details change to 'Audit Team Member (s) | TY/DC/YL | 20/08/2021 | Change Request | Fixed
70 | Focal officer for all 3 processes | Propose audit date, audit type and audit team | TY/DC/YL | 20/08/2021 | Change Request | Open | New Requirement
71 | Audit Team - composition by Focal | Provide option to reconstitute audit team incase of rejection by the client | TY/DC/YL | 20/08/2021 | Change Request | Fixed
72 | Audit Team Leader | After uploading the audit plan, the uploaded file is not visible on the interface. | TY/DC/YL | 20/08/2021 | Change Request | Fixed
73 | Auditing |  | TY/DC/YL | 20/08/2021 | Change Request
74 |  | Do you have any objection on the audit team composition? | TY/DC/YL | 20/08/2021 | Change Request | Fixed
75 | Auditors - Audit Plan | Audit Plan - Send for acceptance - change to - Share with client | TY/DC/YL | 20/08/2021 | Change Request | Fixed
76 | Client | Audit plan attached is under 'Attachment' - write as 'View Audit Plan' | TY/DC/YL | 20/08/2021 | Change Request | Fixed
77 | Client | Remove - accept/reject option under under plan | TY/DC/YL | 20/08/2021 | Change Request | Open | Not Clear
78 | Inspector | At the end of the audit findings: Remove - audit daye, nature of audit, remark from client and remark from focal officer. ADD - Recommendation (TY to send) | TY/DC/YL | 20/08/2021 | Change Request | Fixed
79 | Inspector |  | TY/DC/YL | 20/08/2021 | Change Request
80 | Client - Organic Application | Remove request date for inspection | TY/DC/YL | 20/08/2021 | Change Request | Fixed
81 | Client - Organic Application | Include business license number (if applicable) , name of techical incharge (if different from the owner) and name of management incharge (if different from the owner) ... like in GAP application. | TY/DC/YL | 20/08/2021 | Change Request | Fixed
82 | Client - Organic Application | List drop down units in area /yield unit/sold unit | TY/DC/YL | 20/08/2021 | Change Request | Fixed
83 | Client - Organic Application | Auto balance stock calculation not working | TY/DC/YL | 20/08/2021 | Change Request | Fixed
84 | Client - Organic Application | Add option - to click to next if not applicable | TY/DC/YL | 20/08/2021 | Change Request | Fixed
85 | Client - Organic Application | Standard - remove BhutanGAP Standard and replace with Bhutan Organic Standard (BOS 01:2019) | TY/DC/YL | 20/08/2021 | Change Request | Fixed